## Summary-GroupIterationProgress
This report has 1 group iteration progress summary sheet to be filled at the end of each iteration by the team leader, 1 project ontribution sheet to be filled by everyone at the end of the semester, and 1 weekly report sheet per student.
This sheet should be completed by the team leader (or other member in the team) by the end of each iteration.
iteration | Date range | accomplishment summary (such as user stories/tasks completed/big progress, good practices used, etc) | Technical issues summary | non-technical issues summary | Process improvement/plan | # of user story points completed | # of user story points in progress | # of issues opened | # of issues closed | # of issues remained | Total work time (h) | Total Individual work time (h) | Total group meeting time (h) | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Any other metrics defined in your SPPP
0 | 9.13-9.26 | Project Initiation: Set up the Django framework and GitHub repository. Planning & Design: Defined high-level project features and user stories. Risk Management: Identified potential project risks and mitigation strategies. Related Work: Analyzed existing movie data visualization platforms for comparison. Configuration Management: Established Git branching strategy and CI/CD pipeline using GitHub Actions and Docker. Testing Plan: Outlined testing strategy, including unit, integration, and manual testing with selected tools. Demo Development: Created a demo to showcase basic features and structure. | Limited familiarity with Django framework among some team members, and unfamiliarity with GitHub version control for others, requiring additional onboarding and training. | Task content lacked clear explanation, and team faced limited understanding of certain concepts in the SPPP document, requiring clarification and additional research. | Enhance communication and task allocation by setting clearer assignments and timelines. Leaders will share knowledge and experience to assist team members in unfamiliar areas. Increase the use of Google Drive and GitHub for frequent document and code synchronization. | 0 | 7 | 8 | 4 | 4 | 72 | 70 | 2 | 22 | 11 | 2 | 0 | 0 | 8 | 12
1 | 9.27-10.17 |  |  |  |  | 5 | 5 |  |  | 2
2
3

## Xuansheng Xia
Your Lead Roles: Team Leader, Design and Implementation Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/13-09/19 | 7 | 5 | 2 | 0 - Familiarized with GitHub Desktop and learned version control setup. 1 - Defined the high-level overview for the project proposal. 6 - Set up GitHub repository and configured project environment. | 3 | 1 |  |  |  |  | 1 |  | 1. Initialized GitHub repository with project structure and documentation. 2. Wrote project overview for the SPPP document. | 1. Limited familiarity with Django framework. 2. Difficulty in assigning clear tasks and roles for team members. | 1. Begin Django tutorials to improve proficiency. 2. Collaborate with team members to define roles and distribute tasks. | 0. Continue with Django tutorials and build a basic project example. 1. Outline functional requirements for the SPPP document. | 8
2 | 09/20-09/26 | 8 | 7 | 1 | 1 - Completed functional and nonfunctional requirements for the SPPP document. 5 - Finalized risk management section and communicated with team members. 6 - Improved GitHub repository structure with core files. 7-prepare presentation. |  | 2 |  |  |  | 0.5 | 4 | 0.5 | 1. Finalized the submission of the SPPP document with requirements and risks. 2. Enhanced project structure on GitHub with relevant documentation. | 1. Need further proficiency with Django for code implementation. 2. More clarity required on task distribution. | 1. Continue working on Django tutorials and implement basic Django models. 2. Collaborate with team members for project planning. 3. Conduct next group meeting to finalize task distribution.
3 | 09/27-10/03 | 11 | 10 | 1 | 6 - Finalized database schema and implemented in the development environment. 3 - Developed Python scripts to scrape IMDB data and populate the database. 3 - Created initial data visualization features using JavaScript and ECharts. 4 - Conducted initial testing and debugging of the scraping and visualization functionalities. 5 - Conducted a review meeting to prepare for the final presentation. |  |  |  | 4 | 1 | 1 | 5 |  | Implemented database schema for movie and review data. Developed initial data visualization interface. | Encountered challenges with data consistency during scraping. Minor bugs in visualization scripts. | Adjusted scraping scripts to improve data quality. Debugged and refined visualization functionalities. | Enhance visualization features. Conduct comprehensive testing of the frontend. | 9
4 | 10/04-10/10 | 9 | 8 | 1 | 3 - Enhanced data visualization capabilities with advanced ECharts features. 4 - Debugged and tested new visualization features to ensure data accuracy and presentation quality. 0 - Spent time learning advanced features of ECharts for dynamic visualizations. 5 - Weekly team meeting to discuss project progress and challenges. | 2 |  |  | 4 | 2 | 1 |  |  | Enhanced visualization features with dynamic elements. Streamlined frontend-backend data integration. | Issues with frontend performance under large data loads. Some features not displaying data as expected. | Optimized frontend code for better performance. Corrected data mapping issues in JavaScript. | Finalize documentation and prepare for project presentation. Review all functionalities to ensure seamless operation. | 10
5 | 10/11-10/17 | 8 | 6.5 | 1.5 | 1 - Completed all project documentation, outlining setup instructions, usage guides, and development process. 3 - Finalized presentation materials and ensured smooth integration of all project components. 5 - Final team meeting to discuss project completion and future steps. |  | 3.5 |  | 3 |  | 1.5 |  |  | Completed comprehensive project documentation. Prepared and rehearsed final project presentation. | No significant issues, minor tweaks in presentation slides. | Made final adjustments to presentation based on feedback. | Present the final project. Submit all project deliverables and documentation. | 8

## Xiaojuan Li
Your Lead Roles: Requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/12-09/19 | 7 | 6 | 1 | 0 - Learn git and github, read several tutorials;learn class notes 1 - Get insipirations from similar project, brainstorm requirements 5 - Organize meeting minutes 6 - Set up git and github 7 - Research related work, learn requirements for project documentation | 3 | 1 |  |  |  | 0.5 | 1 | 0.5 | 1. Write Meeting Minutes-Kick Off meeting 2. Set up git, commit a modification on git, complete lab1 3. Prepare for SPPP | 1.As a new team member this week, communication and task assignment is not quite clear yet. 2.Not familiar with some knowledge like risk management, QA metrics | 1.Get more involved in the team and learn more about the requirements next week 2. Review the class notes | 0 - Continue to learn tutorials and notes 1 - Continue requirements analysis 3 - Set up relevant project enviroment 7 - Complete the related work research | 8
2 | 09/20-09/26 | 11 | 10 | 1 | 0 - Learn Django, read tutorials;learn class notes. 1 - Collaborate with leader on requirements analysis, find differences between our project and other similar ones. 5 - Actively involved in meetings and communications by offering some ideas & suggestions. 6 - Set up Django and all related project development environment. 7 - Complete the research of similar products, prepare presentation iter0 and make a live demo if it is doable | 2 | 2 |  |  |  | 1 | 1 | 4 | 1. Write 1 section of SPPP 2. Set up project development environment 3. Draft ppt and prepare for Iteration 0 presentation 4. Design a live demo being connected to a real domain | 1. Not proficient with Django and other tools in framework, need more time to acquire some skills 2. Task assignments in upcoming development is not clear yet. | 1. Finish Related tutorials in two weeks, be able to complete some tasks in Djano and Echart next week 2. Be more active in the discussion toward task assignments. | 0 - Continue to learn related tools 1 - Continue to analyze requirements 3 - Implement more advanced tasks on Django | 9

## Hengyi Song
Your Lead Roles: Security Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/12-09/19 | 6 | 4 | 2 | 0 - get familiar with git 1 - define high level requirements 5 - team meeting 6 - set up git | 2 | 1 | 0 | 0 | 0 | 2 | 1 | 0 | 1. Set up git, commit a test message on git |  |  | 1. Tasks assignements among each team members 2. Reports Writing | 10
2 | 09/19 - 09/26 | 8 | 7 | 1 | 0 - get familiar with django 1 - define high level requirements 5 - team meeting 6 - set up git 7 - researching and reporting writing | 2 | 1 | 0 | 0 | 0 | 1 | 1 | 3 | 1. Write Management Plan section is SPPP 2. Complete Risk Management Spreadsheet |  |  | 1. Clear individual tasks assignements 2. Project Design | 10
3 | 09/27-10/03 | 11 | 10 | 1 | 6 - Finalized database schema and implemented in the development environment. 3 - Developed Python scripts to scrape IMDB data and populate the database. 3 - Created initial data visualization features using JavaScript and ECharts. 4 - Conducted initial testing and debugging of the scraping and visualization functionalities. 5 - Conducted a review meeting to prepare for the final presentation. |  |  |  | 4 | 1 | 1 | 5 |  | Implemented database schema for movie and review data. Developed initial data visualization interface. | Encountered challenges with data consistency during scraping. Minor bugs in visualization scripts. | Adjusted scraping scripts to improve data quality. Debugged and refined visualization functionalities. | Enhance visualization features. Conduct comprehensive testing of the frontend. | 9
4 | 10/04-10/10 | 9 | 8 | 1 | 3 - Enhanced data visualization capabilities with advanced ECharts features. 4 - Debugged and tested new visualization features to ensure data accuracy and presentation quality. 0 - Spent time learning advanced features of ECharts for dynamic visualizations. 5 - Weekly team meeting to discuss project progress and challenges. | 2 |  |  | 4 | 2 | 1 |  |  | Enhanced visualization features with dynamic elements. Streamlined frontend-backend data integration. | Issues with frontend performance under large data loads. Some features not displaying data as expected. | Optimized frontend code for better performance. Corrected data mapping issues in JavaScript. | Finalize documentation and prepare for project presentation. Review all functionalities to ensure seamless operation. | 10
5 | 10/11-10/17 | 8 | 6.5 | 1.5 | 1 - Completed all project documentation, outlining setup instructions, usage guides, and development process. 3 - Finalized presentation materials and ensured smooth integration of all project components. 5 - Final team meeting to discuss project completion and future steps. |  | 3.5 |  | 3 |  | 1.5 |  |  | Completed comprehensive project documentation. Prepared and rehearsed final project presentation. | No significant issues, minor tweaks in presentation slides. | Made final adjustments to presentation based on feedback. | Present the final project. Submit all project deliverables and documentation. | 8

## Ziliang Ren
Your Lead Roles: QA Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/13-09/19 | 6 | 5 | 1 | 0 - learn git 5 - make project plan, find other teammates 6 - set up git 7 - research similar products, | 2 | 1 |  |  |  | 0.5 | 1 | 0.5 | Set up git, commit a test message on git | 1. not familar with Django framework, hard to write any code on it 2. communication is not clear. Task assignments is not clear. | finish all these questions | 1 - continue to define requirements 2.write sppp | 6
2 | 09/20-09/26 | 7 | 6 | 1 | 0 - learning how to provide a better project. 2 - design sppp 5 - communicate with other team members, about how to manage the team work, and which part should members do 7 - relate some other knowledge, like how to test | 1 |  | 2 |  |  | 1 |  | 2 |  | don't know how to fix sppp part 6

## Mingyuan Xu
Your Lead Roles: Configuration Leader
Wee k # | Date range | Total actual time of this week tasks (h) | Total Individua l work time | Total group meetin g time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estima ted time
1 | 09/12-09/19 | 7 | 6 | 1 | 0 - learn git and django, read several tutorials 5 - make project plan, send reminders to team member 7 - research similar products, prepare presentation | 3 | 1 |  |  |  | 0.5 | 1 | 0.5 | 1. Write 3 sections of SPPP 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation | 1. not familar with Django framework, hard to write any code on it 2. communication is not clear. Task assignments is not clear. | 1. finish Django tutorial in 2 weeks, be able to create simple Djano hello world project next week 2. Send task assignments to all members again | 0 - continue to learn Django 1 - continue to define requirements 3 - implement a basic hello world on Django | 6
2 | 9/19-9/26 | 7 | 6 | 1 | 2 - Design Design the configuration management process for the project 6.Initializing and setting up the Git remote repository. | 4 | 1 |  |  |  | 1 | 1 | 1 | 1. Write Management Plan section is SPPP | none |  | 1.project design | 7
3 | 10/04-10/10 | 9 | 8 | 1 | 5 - Weekly team meeting to discuss project progress and challenges. 7-prepare presentation.
4 | 10/11-10/17 | 9 | 7.5 | 1.5

## projectcontribution
This sheet need to be filled by the end of the semester. You should clearly describe your contribution to the group project in each category in the whole semester.
StudentName | SPPP Document | Requirement Analysis on Pivotaltracker | Design Document (SDD) | Testing Documentation (STD) | Presentation | Implementation (code on Github) | Testing (unittest code on Github or manual testing) | Configuration and Deployment | General communication and management | Other Comments

## studentName
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/12-09/19 | 7 | 6 | 1 | 0 - learn git and django, read several tutorials 1 - define high level requirements, 5 - make project plan, send reminders to team members 6 - set up git 7 - research similar products, prepare presentation | 3 | 1 |  |  |  | 0.5 | 1 | 0.5 | 1. Write 3 sections of SPPP 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation | 1. not familar with Django framework, hard to write any code on it 2. communication is not clear. Task assignments is not clear. | 1. finish Django tutorial in 2 weeks, be able to create simple Djano hello world project next week 2. Send task assignments to all members again | 0 - continue to learn Django 1 - continue to define requirements 3 - implement a basic hello world on Django | 6