## Sheet1
This sheet provides some common risks in student projects. You should check if it applies to your group project. You should also feel free to add other risks. Exemplary analysis is also added.
Risk Category | Risk Title | Description | Estimated likelihood of occurrence (L: 1-5 with 1 lowest likelihood) | Estimated Impact (I:1-5 with 1 lowest impact) | Estimated retirement Cost (C: 1-5 with 1 lowest cost) | Priority (lowest number has high priority) (6-L)*(6-I)*C) | Responsible engineer | Target completion date | Detailed plan | Execution summary | Status
personel | Loss team members | One or more team members drop the class | 2 | 4 | 4 | 4*2*4=32 | team leader and all members | Before Iteration 2 due | Redefine the project scope if necessary, and assign the tasks to other team members. | No one dropped the class so far | Open
| add new team members | Communication with external stakeholders has broken down, slowing down project decisions. | 3 | 2 | 2 | 4*2*4=33 | Team Leader | Before Iteration 2 due | Set up weekly meetings with stakeholders to keep communication lines open and transparent. | The project has just started, risk not encountered yet. | Open
| Lack of motivation or responsibility | Team members are not contributing enough due to other obligations or lack of interest | 4 | 3 | 4 | 4*2*4=34 | Team Leader | Before Iteration 2 due | Team meetings will track progress; peer reviews will be conducted to hold accountability and motivation meetings will be organized if necessary | The project has just started, risk not encountered yet. | Open
Communication | duplicate work | Team members unintentionally work on the same component due to miscommunication | 3 | 2 | 2 | 4*2*4=35 | Team Leader | Before Iteration 2 due | Implement a clear task assignment system (using PivotalTracker) to ensure no duplicate work happens, with regular updates at team meetings | The project has just started, risk not encountered yet. | Open
| worked on wrong components | There is a lack of clarity about team roles, which is leading to duplicated work efforts. | 3 | 3 | 4 | 4*2*4=36 | team leader and all members | Before Iteration 2 due | Schedule a time-management workshop to help team members balance workloads more effectively. | The project has just started, risk not encountered yet. | Open
| useless work | Team members are experiencing difficulties with managing their time between the project and other commitments. | 2 | 2 | 2 | 4*2*4=37 | Team Leader | Before Iteration 2 due | Bring in technical experts to resolve ongoing issues with project tools. | The project has just started, risk not encountered yet. | Open
| inconsistent work | Communication with external stakeholders has broken down, slowing down project decisions. | 3 | 2 | 2 | 4*2*4=38 | Team Leader | Before Iteration 2 due | Schedule a time-management workshop to help team members balance workloads more effectively. | The project has just started, risk not encountered yet. | Open
Requirements | unclear requirements | The project scope has grown significantly, causing challenges in keeping tasks aligned. | 4 | 3 | 4 | 4*2*4=39 | Requirement Leader | Before Iteration 2 due | Revisit the project scope with the stakeholders and adjust deadlines accordingly. | The project has just started, risk not encountered yet. | Open
| scope creep | Technical issues are emerging with the tools being used, requiring constant troubleshooting. | 2 | 5 | 2 | 4*2*4=40 | Configuration Leader | Before Iteration 2 due | Revisit the project scope with the stakeholders and adjust deadlines accordingly. | The project has just started, risk not encountered yet. | Open
| constant requirements changes | A key team member has left the project, impacting the overall team performance. | 5 | 2 | 2 | 4*2*4=41 | team leader and all members | Before Iteration 2 due | Recruit a new team member or redistribute tasks among the remaining team. | The project has just started, risk not encountered yet. | Open
Management | improper task assignments | Team members are experiencing difficulties with managing their time between the project and other commitments. | 2 | 2 | 2 | 4*2*4=42 | Team Leader | Before Iteration 2 due | Revisit the project scope with the stakeholders and adjust deadlines accordingly. | The project has just started, risk not encountered yet. | Open
| improper planning | Technical issues are emerging with the tools being used, requiring constant troubleshooting. | 3 | 2 | 2 | 4*2*4=43 | Configuration Leader | Before Iteration 2 due | Revisit the project scope with the stakeholders and adjust deadlines accordingly. | The project has just started, risk not encountered yet. | Open
| lack of management skills | The project scope has grown significantly, causing challenges in keeping tasks aligned. | 5 | 2 | 2 | 4*2*4=44 | Requirement Leader | Before Iteration 2 due | Schedule a time-management workshop to help team members balance workloads more effectively. | The project has just started, risk not encountered yet. | Open
Technology competence | Not familiar with the framework used | Team members are not proficient in Django or the chosen tech stack | 2 | 5 | 2 | 4*2*4=45 | Team Leader | Before Iteration 2 due | Organize training sessions or tutorials on Django; ensure proper documentation is available to help all team members understand the framework used | The project has just started, risk not encountered yet. | Open
| Not familiar with the programming language used | Team members are experiencing difficulties with managing their time between the project and other commitments. | 3 | 2 | 2 | 4*2*4=46 | Team Leader | Before Iteration 2 due | Schedule a time-management workshop to help team members balance workloads more effectively. | The project has just started, risk not encountered yet. | Open
| Not familiar with unit testing | Technical issues are emerging with the tools being used, requiring constant troubleshooting. | 3 | 2 | 2 | 4*2*4=47 | Configuration Leader | Before Iteration 2 due | Bring in technical experts to resolve ongoing issues with project tools. | The project has just started, risk not encountered yet. | Open
| Other technology incompetence | A key team member has left the project, impacting the overall team performance. | 5 | 2 | 2 | 4*2*4=48 | team leader and all members | Before Iteration 2 due | Recruit a new team member or redistribute tasks among the remaining team. | The project has just started, risk not encountered yet. | Open
| Not familiar with Git | Team members lack proficiency in using Git for version control | 2 | 2 | 2 | 4*2*4=49 | Team Leader | Before Iteration 2 due | Git tutorials will be provided; team will adopt GitHub Desktop for easier management, and peer support sessions will be organized | The project has just started, risk not encountered yet. | Open
Design and implementation | Improper design | Initial system design does not meet project requirements or user needs | 3 | 2 | 2 | 4*2*4=50 | Requirement Leader | Before Iteration 2 due | Conduct thorough requirement analysis and get feedback from the customer (or project stakeholders); iterative review of the design during development | The project has just started, risk not encountered yet. | Open
| improper technology stack | A key team member has left the project, impacting the overall team performance. | 2 | 2 | 2 | 4*2*4=51 | team leader and all members | Before Iteration 2 due | Schedule a time-management workshop to help team members balance workloads more effectively. | The project has just started, risk not encountered yet. | Open
| Messy code | Team members are experiencing difficulties with managing their time between the project and other commitments. | 2 | 2 | 2 | 4*2*4=52 | Team Leader | Before Iteration 2 due | Revisit the project scope with the stakeholders and adjust deadlines accordingly. | The project has just started, risk not encountered yet. | Open
Testing | Not enough testing | Lack of sufficient test coverage during development, leading to undetected bugs | 3 | 2 | 2 | 4*2*4=53 | team leader and all members | Before Iteration 2 due | Implement unit and integration testing from early stages; use automated test tools where possible and require code review before merging | The project has just started, risk not encountered yet. | Open
Integration and deployment | Not enough time for integration and deployment | The project scope has grown significantly, causing challenges in keeping tasks aligned. | 2 | 2 | 2 | 4*2*4=54 | Requirement Leader | Before Iteration 2 due | Redistribute tasks among the team. | The project has just started, risk not encountered yet. | Open